MEMO:	Hotel/Motel Summer Plan

TO:		Governor Patrick

FR:		Aaron Gornstein, Undersecretary of Housing

DT:		June 18, 2014

PURPOSE

This memo describes the Department of Housing and Community Development’s (DHCD) summer initiatives that will focus on four areas: regulatory enforcement, shelter diversion, exit strategies, and shelter expansion.  The outcomes of these targeted initiatives will ensure that families have maintained their eligibility for shelter, are diverted from or exit shelter by utilizing the Department’s targeted resources, and that additional shelter beds are available early in FY’15.

BACKGROUND

Since 2009, DHCD has faced an increase in the demand for emergency shelter during the summer months. In FY’14, DHCD experienced record numbers of families seeking shelter with over 673 families entering the month of August alone.

DHCD anticipates a seasonal increase corresponding with the end of the school year. Additionally, at least 590 families will time out of HomeBASE Rental Assistance (HBRA) in the month of June, the final month of HBRA.  In May, 2014, 565 families entered shelter/motels, dramatically exceeding the 485 who entered in April, 2014, and the 388 families who entered in May, 2013.

Residential Assistance for Families in Transition (RAFT), which is a critical bridge for thousands of families each year, ran out of money in early May of this year. The program is expected to start taking new applications once you sign the FY15 budget.

BUDGET UPDATE

The following table summarizes funding levels for key DHCD accounts related to family homelessness:

| Account | Account Name | FY2015 Governor's H2 Budget | FY2015 House Final | FY2015 Senate Final |
| --- | --- | --- | --- | --- |
| 7004-0101 | Family Shelters | 167,344,144 | 125,199,718 | 136,946,602 |
| 7004-0103 | EA Motels/Hotels | 12,299,157 | 15,100,000 | - |
| 7004-0108 | HomeBASE | 24,322,911 | 25,955,535 | 24,203,353 |

Both the House and Senate have proposed funding levels likely to create a deficiency in FY15 for the EA and motel accounts. The Department is obligated to place families who qualify for Emergency Assistance (EA). The Legislature has, in recent past budgets, rejected attempts to place time limits on emergency shelter, and has expanded access by permitting those in irregular housing situations to utilize emergency shelter.  Floor amendments to expand eligibility and to reinstitute short-term (7 day) emergency beds were rejected in both the House and Senate budgets for FY15.

REGULATORY ENFORCEMENT

DHCD has begun implementation of the following enforcement measures, but they will be in full force during the summer months.

- Income Redetermination: The Department will work with its HomeBASE and shelter providers to identify families that have increased their income while in shelter and undertake income redetermination to ensure that the household is still EA income eligible.  Families who are determined to be over income will be targeted for re-housing (families have 6 months to leave shelter based on regulation).

- Removal of Households with No Dependent Children:  DHCD will work with DCF to identify cases where DCF has permanently removed children from the care of parents who are residing in shelters/hotels. These households will immediately be issued a termination notice and removed from their placement.

- Identify Households with Open Warrants:  With the assistance of the Executive Office of Public Safety, DHCD will match EA households with those in the Criminal Justice Information System to identify households who have open warrants.  Families will have 30-days to clear the warrant or they will be determined ineligible for shelter.

SHELTER DIVERSION

- Diversion Benefit Increase to $6,000:  DHCD is currently authorized to utilize up to $4,000 in HomeBASE Household Assistance to help divert families from shelter.  The rehousing benefit is currently being supplemented by up to $2,000 in additional funds from the Housing and Preservation Stabilization Trust, which is not available to families being diverted from shelter. Though both the House and Senate budget give DHCD legal authority to spend up to $6,000 per resident, they do not provide resources to do so.  This is a high priority for implementation and we believe we will be able to utilize the Trust, however, we cannot be certain of the trust fund balance until the conference report is finalized.

- Extend Employment Contracts of HomeBASE Re-Housing Team: The HomeBASE Re-housing staff were brought on in FY’14 to address the potential impact of the over 5,600 households coming off the HomeBASE Rental Assistance benefit.  Due to the Re-Housing team’s efforts, the rate of families returning to shelter has been remarkably low (11%).  ANF has approved DHCD to extend the employment contracts of four contractors through December 2015.  This additional 6 months will enable this staff to continue to do outreach with HomeBASE families to divert them from shelter.

- Hiring of Hotel/Motel Assistant Director:  This new position will provide leadership and direction to the three Transitional Homeless Coordinators assigned to the EA hotels/motels and will direct the summer plan initiatives in these venues.  This position will be filled by mid-June.

- Add Diversion Staff in Boston and Springfield Offices:  DHCD will ask our shelter providers in the Boston and Springfield regions to provide a total of two full-time staff for daily coverage over the summer months to focus on diverting families when they apply for emergency assistance.  This will help to bolster the work of DHCD staff in these offices who need to primarily focus on processing applications.

REHOUSING FAMILIES IN SHELTER

- Issuance of Housing Choice Vouchers:  Boston Housing Authority (BHA) will provide 300 vouchers as part of the Leading the Way Home Initiative.  These vouchers will be targeted to families who were rendered homeless in Boston.  Issuance of these resources will begin in June of 2014.

- Rehousing Benefit Increase to $6,000:  DHCD is currently authorized to utilize up to $4,000 in HomeBASE Household Assistance to help rehouse families in shelter.  This is currently being supplemented by up to $2,000 in additional funds from the Housing and Preservation Stabilization Trust. Though both the House and Senate budget give DHCD legal authority to spend up to $6,000 per resident directly from the HomeBASE account, they do not provide resources to do so. This is a high priority for implementation and we believe we will be able to utilize the Trust, however, we cannot be certain of the trust fund balance until the conference report is finalized.

Shelter Expansion

- Continue Shelter Expansion Efforts:  During FY14, DHCD has increased our congregate shelter capacity by 650 beds, which has helped to reduce the number of families in the motels.  By the end of June, an additional 175 shelter units will be on line, bringing the total number of shelter units to 2,848.

After discussions with your senior team, I recommend moving forward with the expansion of 1,000 additional congregate beds as you have proposed in the FY15 budget.  The Department continues to work with its shelter provider network on identifying available units so that units can be brought on line as quickly as possible.  Based on current caseload projections, DHCD will require an additional $47.5 M beyond the “best-case” conference funding outcome to afford the continued shelter bed expansion efforts as proposed. Notably, if we do not continue our congregate expansion efforts, DHCD estimates that it would still require $45 M to afford underlying caseload demands in FY15.   As such, A&F supports proceeding with our continued congregate shelter expansion efforts.

The following table summarizes the timeline for shelter expansion:

| Month | Number of Units | Associated Costs |
| --- | --- | --- |
| June – FY’14 Supplemental Budget | 175 |  |
| Total – FY’14 |  | $475,000 |
| July | 150 | $6,318,000 |
| August | 200 | $7,722,000 |
| September | 250 | $8,775,000 |
| October | 225 | $7,107,750 |
| Total – FY’15 | 1000 | $29,922,750 |

NEXT STEPS

As outlined above, DHCD is making every effort to stretch its resources and help families rehouse or avoid shelter.  The activities outlined in this summer plan will relieve the pressure we anticipate experiencing in the EA system.  It is extremely important that we focus on a comprehensive approach that includes monitoring, shelter diversion, exit strategies, and congregate shelter expansion.

Once we have received your approval, we will work closely with ANF and your team to notify the Ways and Means Committees, key legislators, and stakeholder groups of our summer plan.